## Sheet1
Sprint 1: One week
Task | Expected (hrs) | Actual (hrs)
Draw architecture of game | 10 | 12
Set up continuous integration | 4 | 2
Create JSON file storing rules of game (Whist) | 3 | 2
Represent each card with enums | 4 | 2
Parse rules from JSON file | 40 | 42
Implement a very simple version of game to be played on one terminal (Hard coded rules) | 50 | 51
Total | 111 | 111
Sprint 2: One week
Task | Expected (hrs) | Actual (hrs)
Translate JSON to a local data structure | 16 | 20
Implement game loop which works with parsed data | 30 | 32
Server that can accept connection from multiple users (Expect up to 4 different sockets) | 40 | 38
Set up client which can connect to a server | 14 | 10
Total | 100 | 100
Sprint 3: One Week
Task | Expected (hrs) | Actual (hrs)
Send messages from localhost to client terminal | 24 | 28
Fixed game loop scoring error | 12 | 14
Create JSON rules for basic game of Spades and Hearts | 4 | 8
Implement method to determine winner/loser of game | 4 | 4
Input control (User cannot play a card they don't own) | 5 | 2
Create some unit tests for basic game functionality | 49 | 56
Total | 98 | 112
Sprint 4: One Week
Task | Expected (hrs) | Actual (hrs)
Adapt game to be played over a network | 36 | 40
Adapt network to be able to send card game rules | 20 | 21
Adapt network to be able to receive card game rules from game host | 20 | 25
Adapt send function from hosting class to handle new line characters | 2 | 1
Adapt client class to handle receiving new line characters | 2 | 2
Implement terminal UI | 3 | 3
Ensure players can not see other player's cards | 2 | 2
Total | 85 | 94
Sprint 5: One Week
Task | Expected (hrs) | Actual (hrs)
Extend unit tests to be more thorough | 10 | 8
Implement simple bidding | 5 | 5
Integrate network into the game logic | 20 | 28
Create basic plan for AI | 10 | 12
Total | 45 | 53
Sprint 6: One week
Task | Expected (hrs) | Actual (hrs)
Create simple REACT interface | 15 | 10
Create protocol for frontend/ backend communication | 15 | 15
Create basic 'AI' | 15 | N/A
Total | 30 | 25
Sprint 7: One week
Task | Expected (hrs) | Actual (hrs) | Planning Poker
Implement socket communication between back end and middleware | 10 | 12 | 3
Implement websocket communcation between middleware and front end | 10 | 12 | 5
Implement UDP to discover other players | 5 | 4 | 2
Adjust game logic to allow for Bridge game | 20 | 22 | 8
Create new JSON games | 5 | 7 | 2
Finish integration of terminal game to web UI | 15 | 20 | 3
Swap random cards (special feature) | 6 | 4 | 2
Total | 71 | 81
Sprint 8: One Week
Task | Expected (hrs) | Actual (hrs) | Planning Poker
Add a exit button functionality to back-end (requires multithreading) | 5 | 15 | 2
Add exit button functionality to front-end | 2 | 5 | 1
Add AI functionality to back-end | 1 | 1 | 0
Add AI functionality to front-end | 4 | 4 | 1
Functionality of bridge added to front (including communication from back-end) | 10 | 10 | 5
Add card skins to front end | 4 | 2 | 1
Modify network infrastructure to allow to host on school servers | 10 | 12 | 3
Add username functionality to front with front end validation | 5 | 6 | 3
Add username field to back-end | 1 | 1 | 1
Allow for cards to be turned over in front-end | 5 | 7 | 5
Add feature which flips card over (back-end) | 10 | 4 | 2
Sort cards on front-end | 15 | 12 | 8
Total | 72 | 79
Sprint 9: One Week
Task | Expected (hrs) | Actual (hrs) | Planning Poker
Work on prettifying User-Interface | 20 | 21 | 3
Improve AI | 10 | 12 | 8
Intuitive Interface | 5 | 4 | 3
Stable Interface | 20 | 21 | 5
Total | 55 | 58