## Sheet1
Sprint 6
Requirement | Status | Priority (1=top priority)
As a player I should be able to play a functional game | In progress | 1
As a player I should have an interface to play on | In progress | 2
As a player my interface should be stable and work smoothly | //TODO | 3
As a player I should be able to play bridge | //TODO | 4
As a player I should be able to automatically discover hosting players | //TODO | 5
As a player I should be able to play against an AI | In progress | 6
As a player I should be able to play several different games | //TODO | 7
As a player I should be able to play on an intuitive interface | //TODO | 8
As a player I should be able to play games specific to a cyber card game | //TODO | 9
As a player I should be able to play a challenging game with an AI | //TODO | 10
As a player I should have an aesthetic platform to play on | //TODO | 11
As a user I should be able to initiate a game with other players | Completed (for now) | 12
As a player I should be able to know the final winner of the game | Completed (for now) | 13
As a player I should be able to receive moves from other players | Completed (for now) | 14
As a player I should be able to send moves to other players | Completed (for now) | 15
As a player I should be able to win or lose a game | Completed (for now) | 16
As a player I should be able to play games involving bids | Completed (for now) | 17