## Sheet1
Sprint 3
Requirement | Status | Priority (1=top priority)
As a player I should be able to play only the cards I own | Next to implement [Game logic] | 1
As a user I should be able to initiate a game with other players | Next to implement [Network/Game] | 2
As a player I should have at least 3 games with different rules to choose from | (Extend) Next to implement [JSON] | 3
As a player I should be able to know the final winner of the game | Next to implement [Game logic] | 4
As a player I should be able to win or lose a game | Next to implement [Game logic] | 5
As a player I should be able to play without being interrupted by another player during my turn | //TODO | 6
As a player I should be able to play without seeing other player’s cards | //TODO | 7
As a player I should be able to play against a simple AI | //TODO | 8
As a user I should be able to form a connection to other players | Completed (for now) | 9
As a host I should be able to set the rules of a game | Completed (for now) | 10
As a user I should be able to join a card game | Completed (for now) | 11
As a player I should be able to receive the rules of the game joined | Completed (for now) | 12
As a player I should be able to choose a card to play | Completed (for now) | 13